## Power Map
Stakeholder Map For One Decision
Decision | Merge three regional sales academies into one national programme
Signed off by, and date | Chief Commercial Officer, executive committee on 14 March
Name or role | Position on the decision | What they stand to lose | Detail | Stance | Evidence for the stance | Who they listen to on this | Power (1-5) | Interest (1-5) | Next conversation, with date
Chief Commercial Officer | Decision holder | Nothing identified | Wants one sales standard nationally | Unknown | Has not commented | Head of Sales Operations, on anything involving cost | 5 | 4 | After the Head of Sales Operations, 1 March
Finance Director | Consent holder | Budget or headcount | Controls the budget round | Neutral | Asked twice about academy cost per head | Chief Executive | 4 | 2 | Cost per head comparison, 20 February
North Regional Director | Consent holder | A position taken in public | Set up the northern academy four years ago | Opposed | Said the north needs its own programme | His lead trainer | 4 | 5 | Design that keeps the academy name and lead trainer, 24 February
South Regional Director | Affected | Budget or headcount | Loses two trainers, gains a shared curriculum | Supportive | Proposed sharing materials last year | Peers on the regional board | 3 | 4 | Ask to speak for it at the committee, 3 March
Head of Sales Operations | Influencer | Control of their area | Owns the productivity data the CCO quotes | Unknown | None yet | Finance Director | 3 | 3 | First conversation, 14 February
Regional trainers | Affected | Control of their area | Their roles change | Doubtful | Concerns raised in the last team meeting | Their regional directors | 1 | 5 | Briefing after the committee, 15 March
Free template from Talentient. The full method is part of Trusted Talent Advisor: talentient.com

## Grid
Power And Interest Grid
Calculated from the Power Map. High means 4 or 5. The grid suits long projects; the Power Map suits a single decision.
Name or role | Power | Interest | Quadrant | Treatment

## Positions
The Four Positions
Position | Who it is
Decision holder | The person who signs the decision off
Consent holder | Someone who can veto or delay it, often through a budget or a process they control
Influencer | Someone whose view the decision holder and consent holders trust
Affected | People who will implement the decision or absorb its cost
Rule | Talk to the people who can stop the decision before the person who signs it, and to the people they listen to first.

## How To Use
How To Use The Map
Step | What to do
1 | Name one decision, who signs it off and the date. One map per decision.
2 | List everyone who can sign, stop, shape or absorb the decision, and give each a position.
3 | Record what each person stands to lose, and their stance from what they have said or done.
4 | Fill in who each person listens to on this subject. This column decides the order of conversations.
5 | Score power and interest from 1 to 5 to see the grid view on the Grid sheet.
6 | Book the next conversation with a date for every Unknown, Doubtful and Opposed row, starting with influencers and consent holders.